Appendix X. Final Evaluation - Spanish Language Outreach Program

Spanish Language Outreach Program

Final Evaluation Report

November 2008

Submitted by Janet Salm

WebJunction Evaluator

Table of Contents

EXECUTIVE SUMMARY	3

METHODOLOGY	6

FINDINGS	7

Goal 1. In participating libraries, increase the number of activities directed at reaching Spanish-speaking residents.	7

New Outreach to Spanish Speakers	7

New Computer Classes for Spanish Speakers	8

Changes in frequency of use or programs utilized on public access computers	9

Goal 2. Improve the attitude, knowledge, and skills of local library staff toward outreach to Spanish-speaking residents, with the longer-term goal of increasing the numbers of Spanish speakers involved in public access computing at their local libraries.	10

Goal 3. Increase partnerships among local libraries and other community organizations serving Spanish-speaking residents.	12

Goal 4. Impact the Hispanic community by increasing awareness about local library services and public access computing.	13

Measuring impact on the Hispanic community: Focus groups	13

Marketing library services to the Spanish-speaking community	14

Improvements to library marketing strategies to Spanish speakers	14

Goal 5. Continue to build and grow the Spanish Language Outreach online community at WebJunction for library staff to share content and information with each other, with the longer-term goal of providing access to materials with a larger audience of local libraries through WebJunction.	15

CONCLUSION AND RECOMMENDATIONS	17

# EXECUTIVE SUMMARY

WebJunction's Spanish Language Outreach Program delivered 376 workshops in 36 states across the country, training over 5,000 library staff. The goals of the Spanish Language Outreach Program were:

- In participating libraries, increase the number of activities directed at reaching Spanish-speaking residents.

- Improve the attitude, knowledge, and skills of local library staff toward outreach to Spanish-speaking residents, with the longer-term goal of increasing the numbers of Spanish speakers involved in public access computing at their local libraries.

- Increase partnerships among local libraries and other community organizations serving Spanish-speaking residents.

- Impact the Hispanic community by increasing awareness about local library services and public access computing.

- Continue to build and grow the Spanish Language Outreach online community at WebJunction for library staff to share content and information with each other, with the longer term goal of providing access to materials to a larger audience of local libraries through WebJunction.

WebJunction met and exceeded all of these goals. This report includes complete final data for all three rounds of the Spanish Language Outreach Program. Impact was measured by a series of assessments that were required of all participants: a pre-assessment (taken one to two weeks prior to the workshop), workshop evaluation (administered immediately following the workshop), and a post-assessment (at five months post-workshop). Trainers also completed a pre- and post-assessment. Ten focus groups were conducted with Spanish speakers in communities where new outreach efforts were reported.

Results for each goal are described in detail in this report (see Findings section), and below are summaries of the widening circle of impact on participants, libraries, and the Spanish-speaking community, as well as the internal impact of the SLO evaluation efforts.

Impact on Participants

In changing the attitudes, knowledge and skill levels of workshop participants, the curriculum appears to be successfully introducing and explaining cultural differences between Spanish speakers and mainstream Americans. Participants also gained skills in performing needs assessments so that they can tailor library collections, programs and services to meet Spanish speakers’ needs, and build strategies for effectively reaching out to the Spanish-speaking community (see Findings, Goal 2).

WebJunction’s model for rolling out the Spanish Language Outreach Program featured building the capacity of trainers and coordinators from each state to help library staff learn how to do effective outreach and build strong community partnerships. This meant building the experience, skills and knowledge that will remain in each state for future efforts at reaching out to Spanish speakers or other disenfranchised groups.

After the workshops, trainers, coordinators and participants can participate in follow-on activities within their states or with WebJunction, including webinars to further build skills like using census data and creating ESL conversation clubs. Participants are increasingly visiting WebJunction’s thriving online community of practice related to Spanish Language Outreach that includes WebJunction’s discussion boards, courses, articles and other resources (see Findings, Goal 5).

Impact on Libraries and the Spanish-Speaking Community

Almost 80% of workshop participants have undertaken new outreach activities based on the Spanish Language Outreach workshops, with the most popular activities being new signage, new marketing efforts and new programs / classes (see Findings, Goal 1).

Participants have improved their library’s marketing strategies by following the SLO program curriculum’s recommendation to begin outreach efforts by understanding the local community’s needs and by building partnerships with trusted community organizations that serve Spanish speakers (see Findings, Goal 3). In addition, participants report using the workshop how-to’s to improve the effectiveness of their marketing to the Spanish-speaking community with strategies like focusing on Spanish radio and sending flyers home with school kids (see Findings, Goal 4).

In addition to new outreach and improved marketing efforts aimed at reaching Spanish speakers, about one-quarter (26%) of workshop participants report offering programs and services especially for Spanish speakers. These programs and services include computer classes in Spanish, ESL classes and discussion groups, and cultural heritage celebrations at the library. At six months post-workshops, the blend of services has changed somewhat: the percentage of participating libraries offering open computer lab hours with a Spanish speaker available increased from 15% to 22%, and many library staff report translating existing computer programs into Spanish. Additionally, many library staff report a shift in attitude or a new level of awareness or patience when supporting Spanish-speaking patrons (see Findings, Goals 1 and 4).

Building community partnerships with organizations that serve Spanish speakers is a focus of the curriculum and the SLO Program as a whole, and 43% of workshop participants report starting a new partnership or strengthening an existing partnership (see Findings, Goal 3).

Impact on SLO Program Staff and WebJunction

In addition to measuring the impact of the program, the evaluation results are used internally by program staff to make improvements to the program and to validate and revise the curriculum. Program staff used the evaluation results to guide the revision of the curriculum for Rounds 2 and 3, and results show that the revisions had positive effects, yielding improved ratings on workshop evaluations for Rounds 2 and 3, with approximately 80% of Round 2 and Round 3 workshop participants reporting that the workshops met or exceeded their expectations, as compared with 63% for Round 1.

The Spanish Language Outreach Program has had a strongly positive effect on the WebJunction community and on the sustainability of the WebJunction organization. SLO program participants have been very active participants in the WebJunction community. The SLO Program has been a key driver of site traffic to WebJunction.org. The SLO webinar series (22 webinars to date) has been very popular, and more than 4,000 library staff subscribe to the monthly SLO email newsletter. The workshop has also been adapted into an online course, and 440 people have enrolled since the course went online in March 2006.

RECOMMENDATIONS

Because WebJunction is uniquely positioned with a national perspective on Spanish speakers, SLO staff should continue their efforts to build best practices, host special events and build the community of practice around better serving Spanish speakers, and take advantage of any opportunity to help the library field understand the challenges and success of Spanish speakers in the U.S.

Now that the program’s goals have been achieved, the resources that have been developed by program staff, participants, trainers and consultants can be leveraged. Key resources:

- Curriculum: The SLO Program curriculum, especially community partnership development strategies and effective marketing techniques for reaching out to Spanish speakers, has been validated by community members via focus groups and Perceptions survey data.

- Online community and resource collection: WebJunction’s online collection on outreach to Spanish speakers is a recognized national source of tools and information, cited as a resource even by REFORMA, the key national association to promote library and information services to Latinos and the Spanish speaking. WebJunction should continue to build the collection and the community around the collection, using webinars, newsletters and other methods.

- Understanding of the current “state of the nation” for library staff knowledge, skills and abilities (KSAs) related to outreach to Spanish speakers.

- Trainer cohort: The 158 trainers and coordinators are a ready source of on-the-ground knowledge and insight and should be considered an important national resource that can be used in the future to roll out additional programs or to advise on future efforts and investments needed in this area.

- The Latino Perceptions survey instrument and baseline data on Latino library use and perceptions of libraries can be used to measure progress at local or national levels in reaching out to Spanish speakers.

WebJunction should consider focusing on seeking additional grants and investing in continuing to run on-the-ground national programs – it has been the best source of loyal, interested membership, goodwill and collection development to date.

# METHODOLOGY

The evaluation approach to evaluating the Spanish Language Outreach Program includes measuring changes in participants prior to the workshop and at five months post-workshop, tracking what library staff undertake in their libraries as a result of the workshops, tracking trainer feedback via assessments and interviews, and contacting Spanish-speaking library patrons and library community partners to understand the impact of the results of the workshop on them.

Evaluation and assessments are used for two main purposes – to understand the impact of the program and to provide ongoing feedback, especially at critical junctures like curriculum revisions or major events like Trainer Institutes; and to measure and report progress on the grant. As much as possible, results of the data and lessons learned are shared with Spanish Language Outreach (SLO) program participants and trainers and with the online community at WebJunction.

The instruments used to assess the impact of the program on library staff and their outreach activities are a pre-assessment taken online prior to the workshop, a workshop evaluation sent by trainers and completed online within one week of the workshop, and an online post-assessment sent to participants by WebJunction at five to six months post-workshop. Additionally, trainers completed similar assessments to capture their feedback on the program and curriculum overall. In addition to the formal participant and trainer assessments, phone interviews with trainers were conducted in Rounds 1 and 2 to elicit additional feedback about the curriculum. To assess the effects of the program in the community, six in-person focus groups were conducted with Spanish speakers in representative communities where outreach took place.

The response rates for participant assessments for all three rounds were excellent, at 70% for the pre-assessment, 41% for the post-assessment and 42% for the workshop evaluation.

# FINDINGS

## Goal 1. In participating libraries, increase the number of activities directed at reaching Spanish-speaking residents.

### New Outreach to Spanish Speakers

Based on the SLO workshops, 79% of workshop attendees responding to the post-assessment did new outreach activities or plan to do new outreach activities in the next six months. The main outreach activities they undertook in their libraries were:

- New signage (41%)

- Marketing (35%)

- New programs and classes (32%)

In addition, approximately one-quarter of participating library staff have taken on new internal initiatives related to outreach to Spanish speakers, including planning / needs assessment (26%) and staff development (22%).

Establishing partnerships in the community was one of the main strategies shared in the SLO workshop curriculum, and almost 30% were able to forge new relationships in the community by attending or hosting a community event to promote the library or they invited a community group into the library for a tour (21%).

For those participants who were not able to do new outreach activities based on the workshops, they shared the barriers they’ve faced since their workshops (measure asked on Round 1 data only):

- First and foremost was “lack of time”: 70% of those who did not do new outreach activities after the workshop cited “lack of time” as the reason they hadn’t been able to do any new outreach work.

- Next was “lack of staff capacity to implement new outreach.”

- Additionally, 29% said lack of funding was a barrier to doing more outreach.

- Only 14% cited “lack of support from my administration or board,” which is encouraging.

One of the key improvements to the SLO program was made after Round 1 post-assessment data showed that participants were not very likely to say that they’d put together an action plan by the end of their workshop – only 12% of Round 1 participants said they’d developed an action plan for outreach to Spanish speakers.  Program staff revised the curriculum to link the action plan to each module of the curriculum, to ensure that participants would leave the workshops with a draft action plan in hand. Anecdotally, trainers reported that participants were creating action plans as a part of each workshop, and post-assessment data for Rounds 2 and 3 confirmed the anecdotal data, showing that fully 38% of participants developed action plans.

### New Computer Classes for Spanish Speakers

About one-quarter (26%) of workshop participants report offering programs and services especially for Spanish speakers. These programs and services include computer classes in Spanish, ESL classes and discussion groups, and cultural heritage celebrations at the library.

While the overall percentage only increased by one percent at six months post-workshops, the blend of services has changed somewhat: the percentage of participating libraries offering open computer lab hours with a Spanish speaker available increased from 15% to 22%, and many library staff report translating existing computer programs into Spanish.

Here are the types of computer classes currently offered to Spanish speakers in participating libraries (little change in emphasis from pre- to post-workshop):

- Basic computer skills (84%)

- Internet/searching the web for information (72%)

- Classes on how to use email (60%) (*only asked on R2 and R3)

- MS Office Word and other common applications (48%)

- ESL tutorials (24%)

- Open lab hours with a Spanish speaker available to help (22%)

Because the overall percentage of library staff saying that they offer computer classes for people who speak Spanish remained the same in the six months from the pre-assessment to the post-assessment, extra time was spent trying to understand what did change as a result of the workshops by studying responses to the open-ended question, “Describe any changes in computer classes/workshops for Spanish speakers that occurred in your library as a result of the Spanish Outreach training.”

Many participants did describe direct changes or developments in programs as a result of the training. The most frequently mentioned change was a refinement of computer classes that were already offered by libraries – new applications or levels added or existing trainings translated into Spanish language trainings:

- “Weekly classes taught in Spanish are full. Attendance for programs targeting Spanish speakers is at an all-time high.”

- “We added a second Internet Basico class to serve the 8 extra sign-ups. Now have 2 weekly classes for 8 students each.”

Additionally, some participants reported changes as a direct result of the workshop that will lead to better serving Spanish speakers, like a shift in attitude or a new level of cultural awareness or patience when supporting Spanish-speaking patrons:

- “There is a much more "mellow" vibe with the Spanish speaking visitors who use the computers now. Our understanding of their culture and information needs have simplified the whole process!”

- “I am more patient and encourage patience with Spanish speaking customers. I'm aware of a lot more helpful things I can suggest to them.”

- “We have more Spanish speaking users, because we are allowing two customers at a computer.”

- “I have seen a significant increase in the amount of Spanish speakers that come in to use the library, including public access computers. It is important that they see friendly faces, especially someone that is able to speak Spanish. Otherwise, they seem easily intimidated. More than anything, though, it is important that they are welcomed and appreciated rather than treated as a burden, of which so many are accustomed.”

### Changes in frequency of use or programs utilized on public access computers

While it is difficult to determine direct results of increased use on public access computers via community outreach, many participants reported a shift in attitude or a new level of awareness or patience when supporting Spanish-speaking patrons. Many participants shared small successes; for example, the chance to help one person connect with the right online or community resource, or to help a new computer user create an email account. Others shared larger successes such as full computer classes, incoming requests for specific classes like word processing, and new community partnerships with organizations that provide computer classes.

- “We have seen a definite increase in the use of our computers by Spanish speakers. In fact, entire families are now coming to the library to use our computers and do other things available to them here.”

Participants in Rounds 2 and 3 gave feedback that shows a strong trend toward Spanish speakers using the Internet more for social networking and accomplishing important life tasks, including paying bills online, job applications, consulate appointments, immigration forms, and accessing student loan application forms.

- “Women becoming more confident with computers and figuring how computers can be useful in their lives. Invitations, announcements, resumes, menus, posters, food handlers’ cards, Mexican consulate appointments.”

Highlights from the Workshop Evaluations

In addition to measuring the outcome of increasing library outreach and new programs and services for Spanish speakers, we measured an important process indicator: how well the workshops teach participants how to do outreach and improve programs and services. The workshop evaluation is administered within one week of the workshops, and a report on the prior Round’s workshop evaluations was shared with SLO program staff to inform curriculum revisions. Feedback from participants and trainers was also shared with incoming trainers at the Train the Trainer Institute. Workshop evaluation data is based on 2,281 responses for all three rounds of the program (42% response rate).

Because of the workshop, I:

▪ better understand the benefits and challenges of reaching out to serve Spanish speakers (83%).

▪ better understand what culture is, how we learn it and how it impacts our behavior and 
perceptions (77%).

▪ am more aware of cultural differences, behaviors, and values of mainstream American 
culture and Hispanic/Latino culture (80%).

▪ learned about developing services to meet the needs of Spanish speakers in my community (82%).

▪ learned techniques to build community partnerships and collaborate with the 
Spanish-speaking community (78%).

▪ learned techniques for marketing the library to the Spanish-speaking community (76%).

▪ learned how to find resources and support for Spanish-language outreach at WebJunction.org (86%).

▪ learned how to develop an action plan for reaching out to the Spanish-speaking community (75%).

▪ feel inspired to take action (79%).

## Goal 2. Improve the attitude, knowledge, and skills of local library staff toward outreach to Spanish-speaking residents, with the longer-term goal of increasing the numbers of Spanish speakers involved in public access computing at their local libraries.

Workshop participants answered a series of scaled questions related to their attitudes, knowledge and skills on the pre-assessment prior to attending the workshops and then again six months later – these questions are based on the California State Library’s Cultural Diversity Awareness Self Assessment Guide (Bill Slager, 1994). Participants are asked to rate themselves in three dimensions: “as an individual, as a library employee, and as a leader of outreach in my library.” An important caveat is that measuring attitudes where some attitudes are more socially acceptable tends to skew results towards more positive results.

As can be seen in the chart below, overall, the participants increased their skills and improved their attitudes and beliefs, on average improving between one-third and one-half of a level on a scale from 1 to 5, with 1 being “not like me” and 5 being “very much like me” (the higher the rating, the better).

| As an individual, I: 1 - Know benefits of reaching out to Spanish-speaking customers 2 - Know challenges of reaching out to Spanish-speaking customers 3 - Understand how culture can impact our behavior and perceptions 4 - Understand the culture of the Spanish-speaking customers 5 - Understand difference in behaviors** 6 - Recognize differences between culture** As a library employee, I: 7 - Know how many library customers in my community speak Spanish at home 8 - Know from which countries the Spanish speakers in my community come 9 - Know what challenges Spanish-speaking customers face in my community 10 - Have helped Spanish speakers use the library's public computers 11 - Am able to refer Spanish-speaking patrons to orgs. that meet needs library cannot | As a leader or supporter of outreach, I: 12 - Can articulate the library's goals and objectives especially as they relate to cultural diversity 13 - Can name organizations which specialize in working with Spanish speakers in my community 14 - Have participated in my library's planning for reaching out to people who speak Spanish 15 - Feel that community partnerships are helpful to reaching out to Spanish-speaking customers 16 - Have contributed to building a culturally diverse staff in my library** 17 - Share information with other staff members about how to serve the Spanish-speaking community 18 - Encourage others with whom I work to participate in outreach activities designed to reach Spanish-speaking customers 19 - Have the support of my organization and supervisor to plan and implement outreach activities to Spanish-speaking customers 20 - Have the tools and resources needed to support outreach efforts to Spanish speakers ** denotes measure not asked on all 3 rounds. |
| --- | --- |

In the chart above, those measures with the strongest improvement (of more than .5 on the scale) are indicated by the boldface text in the legend. As can be seen, participating library staff made gains in their individual abilities to understand differences in behaviors in the library (like wanting to work in groups at the computer instead of individually) and are more able to refer patrons to organizations in the community that can meet those needs the library cannot (immigration services, legal services, etc.).  Most impressive is that participating library staff made distinct improvements in almost every measure of their skills, knowledge and abilities related to reaching out to Spanish speakers in their communities.

The chart shows that four measures did not change greatly after the workshops. The reason for the lack of change appears to be either that the measure was related to attitudes and beliefs that may be deeply held and difficult to change, as with measure 3 (“Understand how culture can impact our behavior and perceptions”) and measure 15 (“Feel that community partnerships are helpful to reaching out to Spanish-speaking customers”). Measure 19 may not have shown great change because it relates not to the person attending the workshop, but to the support of supervisors or the organization (“Have the support of my organization and supervisor to plan and implement outreach activities to Spanish-speaking customers”).

## Goal 3. Increase partnerships among local libraries and other community organizations serving Spanish-speaking residents.

New and Strengthened Community Partnerships

As a result of the Spanish Language Outreach Program, 43% of participants either started a new community partnership or strengthened an existing community partnership. Thirteen percent (13%) of workshop participants report establishing a new partnership with community organizations serving the Spanish-speaking community as a result of participating in the SLO workshops. An additional 30% report strengthening an existing partnership as a result of the workshop.

Participants were asked to describe the organization and their partnership. Many participants reported partnerships and alliances with multiple community organizations to share information about different services to all their clients (and data below reflect that participants could “check all that apply” to describe their partnerships).

What type(s) of organizations is the partnership with?

- Schools [preschools, elementary, teens] (55%)

- Adult education programs [community colleges, ESL programs, parenting classes] (53%)

- Health and human service organizations (36%)

- Neighborhood Groups / Partnerships with Individuals (29%)

- Religious organizations (28%)

- Hispanic Chamber of Commerce / Business development organizations (16%)

- Media partnerships (12%)

- Other (12%)

- Legal / Immigration rights organizations (10%)

Schools and Adult Education Programs were the most common partners for participants. Here are some examples of the partnerships the libraries formed:

Schools

- “Our library will be partnering with the local elementary schools in our town. These schools serve the K-5th grade population. The ELL teacher works with students that are ELL learners. Currently there are six children whose primary language is Spanish. We will be establishing and maintaining an organized homework club. The ELL learners will be paired up with homework buddies. Also, the ELL teacher identified that what students and their families benefit from is listening to books on tape. The library will purchase audiobooks in English (popular and classic titles), and develop an annotated bibliography of these titles.”

- “We formalized an acquaintance with the ESL teachers and the school district in regards to their Spanish Language services. They have helped us to become more aware of the issues that face this community and have provided introductions with key people that are willing to work with us on program ideas and language skills. We are still developing this relationship.”

Adult Education Programs

- “Adult Education Program which offers classes in ESL and other career skills. We promote their programs through fliers and word of mouth at the library (we're asked about this kind of program often), and they help advise us on what to buy for Spanish materials, and making contacts in the community.”

- “Beaumont Adult School -- worked with their EvenStart parents last year here at the library and this year working with the parents who leave their child at the school's child care facility. We have a once a month interactive literacy time where I bring books and read one and do a follow-up activity with the parents and children.”

## Goal 4. Impact the Hispanic community by increasing awareness about local library services and public access computing.

### Measuring impact on the Hispanic community: Focus groups

WebJunction conducted focus groups for Rounds 1 and 2 in order to help assess the impact of the Spanish Language Outreach workshops on the local Spanish-speaking communities of participating library staff. The focus groups were designed especially to elicit if community members had noticed any differences in their library following their local library’s staff attending the one-day SLO workshops.

It is very difficult to assess the community impact of a program that is aimed at library staff cultural competencies and outreach strategies. Patrons may or may not notice changes in the library such as signage, flyers for community events, radio advertising or new classes and programs. In order to increase the chances that Spanish-speaking patrons noticed changes in the libraries, we selected those locations where library staff had attended and had conducted new outreach based on the workshops that might be noticeable to patrons: either new signage, new classes or programs for Spanish speakers, or new marketing efforts in the community or local Spanish-speaking media. We also arranged for the focus groups to be added on to regular library events like ESL classes, computer classes, or storytimes, with the aim of recruiting participants who are regular library users, and who might notice changes in the library.

For both rounds, in only one of the three locations where we conducted focus groups did patrons notice changes in the library based on the SLO workshops. In Round 1, participants were likely to identify services and changes that were either not new, or unrelated to the SLO Program. In Round 2, two of the three locations had well-established outreach to Spanish speakers, so it was difficult for focus group participants to identify “new” changes in outreach, programs and services even though locations were chosen where library staff had undertaken new efforts.  Overall, Round 2’s participants noticed more programs and services for Spanish speakers and outreach efforts without prompting, noting a lot of “more this” and “better that” according to our moderators. This may be due to Round 2 having a stronger curriculum, having benefitted from improvements made on the basis of prior focus groups, interviews with trainers, and assessments from trainers, coordinators and workshop participants.

What the focus group participants were able to share with the SLO Program was their input on what it would take to bring more Spanish speakers into the library. They shared their suggestions on what they’d like to see and what strategies they think would be most effective for reaching out to the Spanish-speaking community. In both rounds of focus groups, participants validated that the outreach strategies recommended in the SLO curriculum are optimal. Their suggestions confirmed that the SLO workshop curriculum is right on target – partnering with community organizations is one of the very best ways to reach Spanish speakers, understanding cultural differences and the diversity within Spanish-speaking communities is very important, and celebrating Latino cultural events at the library and in the community would be much appreciated and a great way to build trust and connections. See WebJunction’s SLO Program May 2007 Interim Report and the December 2007 Report on Round 2 Focus Groups for more detail on results.

### Marketing library services to the Spanish-speaking community

At six months post-workshop, there was a slight increase in the percentage of library staff reporting that their library markets services to the Spanish-speaking community (from 59% to 65%). The marketing activities that the libraries are engaging in are similar from pre- to post-workshops and focus on the following activities (in order of prevalence):

- 75% of participating libraries distribute flyers in Spanish for services/classes,

- 54% promote services through organizations that serve Spanish speakers in the community (churches, schools, advocacy groups),

- 45% make information available in Spanish on their library website,

- 36% advertise with Spanish media, and

- 31% include information about Spanish services in library newsletters.

### Improvements to library marketing strategies to Spanish speakers

Participants were asked in an open-ended, essay question to describe any changes resulting from the Spanish Language Outreach training in the way the library markets services to the Spanish-speaking community. Many respondents reported strengthened connections with local schools. Others reported concerted efforts to advertise in Spanish through Spanish-serving organizations, and sharing flyers and information with local Spanish media and radio stations, grocery stores and businesses. There was also recognition by some respondents that attending community events for person-to-person marketing and relationship building was even more valuable than flyers. Some libraries inaugurated their community-leader interviews, others shared that their library was taking into consideration the needs of the Spanish-speaking community when planning book displays, quarterly newsletters, culturally relevant programs, holiday events or activities.

- “Have launched a basic Spanish mini-website that offers access to database content and legal, health, and on-line newspaper links.”

- “We have created flyers written in Spanish, which we distribute in areas we didn't used to: On public transit, at laundromats and grocery stores in our community.”

- “When a program is planned for the Spanish speaking community, our library system (not just the branch I work for) plans programs that are more family oriented. Programs are scheduled when the entire family can attend.”

## Goal 5. Continue to build and grow the Spanish Language Outreach online community at WebJunction for library staff to share content and information with each other, with the longer-term goal of providing access to materials with a larger audience of local libraries through WebJunction.

Resources on WebJunction.org

In the workshop evaluations, participants ranked WebJunction’s online resources as the top “one new thing you learned at the workshop that you know you will use.” In fact, the strong positive comments and reviews of WebJunction by Round 1 participants encouraged a new focus on orienting participants to WebJunction’s resources in the curriculum for the rest of the program.

Over the life of the SLO program, WebJunction has increased the size of the Spanish Language collection each year, adding 79 new items from May 2006 to April 2007 and adding 177 items from May 2007 through July 2008. The collection now includes:

- 51 topic pages full of resources and links (such as “Signage for Spanish-speaking Patrons,” “Citizenship & Immigration,” “Families, Teens & Kids”).

- 434 downloadable resources for library staff (library card application samples in Spanish, MP3s of Survival Spanish for Librarians, computing guides in Spanish).

- 227 articles on issues related to serving Spanish speakers in the library (e.g., “Funding for Programs and Services to the Community,” “Four Keys to Successful Marketing to Spanish Speakers,” “Finding and Evaluating Online Health Information for Spanish Speakers”).

These resources, many of which have been contributed by program participants, include handouts, lesson plans, case studies, research, webinar archives, and additional links to help library staff design and implement outreach to Spanish speakers.

As can be seen in the chart below, site traffic grew with each round. The Spanish Language Outreach homepage has reached WebJunction’s overall top 10 most visited pages five times, and many of SLO’s articles and resources have been in the top 10 articles over the past year. Especially popular has been SLO’s article on “Survival Spanish for Librarians,” which reached the top ranking for most popular article read on WebJunction, and was in the top 10 for three months in a row.

With the launch of the new WebJunction in August 2008, the full Spanish Language Outreach collection was migrated to the new platform. While the number of pageviews is not directly comparable to historical data (different tracking method), the post-launch traffic patterns show consistent monthly traffic, with about 9,000 views of the collection since launch.

With the new platform, WebJunction members can now affiliate themselves with the community of practice related to Spanish Language Outreach. Since launch, 226 WebJunction members have affiliated with SLO.

SLO top 10 most viewed pages (since August 2008):

- Spanish Basic Computer Skills

- SLO Webinars

- Survival Spanish for Library Staff : download

- SLO Workshop Materials

- Spanish: Computers & Technology

- Spanish: Changing the Computer’s Language

- Spanish for Library Staff

- Spanish: Information for Patrons

- Spanish: Internet and Email Skills

- SLO Discussion Boards

In addition to the website resources and discussion boards, participants in the SLO program can build on their workshop experience by attending a follow-on webinar. To date, 22 webinars have been conducted with an average of 50 attendees, on topics from “Needs Assessment” to “Best Practices in Translation;” and the archives can be watched on demand. Over 4,000 people have subscribed to the monthly SLO email newsletter. The workshop has also been adapted into an online course, and 440 people have enrolled since the course went online in March 2006.

Spanish Language Outreach Message Boards Traffic

The SLO discussion boards grow richer as each workshop’s participants are oriented to them – over the course of the project, there have been a total of 602 posts on 338 topics, and those posts have been viewed more than 800,000 times. Workshop participants were asked to share information about their use of the discussion boards on the post-assessment. Almost half (47%) of all participants said that yes, they have used the discussion boards. On the assessment, they were allowed to select only one option, with the goal of pushing them to describe the highest level of participation achieved. Most have been to the discussion boards “just to read and learn,” but 1% said they’d posted a question or topic, 1% said they’d posted an answer, and an additional 1% said they’d posted an opinion. Research on online communities shows an expected 1% contribution rate, so an active contribution rate of 3% is excellent.

Slightly more than half (53%) of the SLO participants said that no, they did not read or post on the SLO discussion boards. We wanted to understand the barriers to using the discussion boards, so this question was worded aggressively to pinpoint any difficulties and improve the instruction next time. The reason library staff members cite not being able to utilize the discussion boards was very clear: “It’s great but I have no time to use it!” After studying feedback from Round 1, documentation on using the discussion boards was improved, and trainers/coordinators were asked to remind their participants to visit the discussion boards, which decreased the percentage of library staff reporting that they didn’t know about the discussion boards or how to access them, or reporting that they’d experienced problems:

- No time (65%)

- Didn’t know about them (10%)

- Didn’t know how to access (5%)

- Tried but had problems (3%)

Feedback about what works well on the discussion boards centered on an appreciation for finding valuable ideas and the opportunity to share experiences with distant colleagues. In terms of the tools available on the message board, participants noted that setting a watch was useful, as was receiving reminders by email (newsletter from SLO), and the search option to make sure a topic is truly new before posting.

# CONCLUSION AND RECOMMENDATIONS

WebJunction met and exceeded all five original program goals:

- In participating libraries, increase the number of activities directed at reaching Spanish-speaking residents. Almost 80% of workshop participants have undertaken new outreach activities based on the Spanish Language Outreach workshops, with the most popular activities being new signage, new marketing efforts and new programs / classes.

- Improve the attitude, knowledge, and skills of local library staff toward outreach to Spanish-speaking residents, with the longer-term goal of increasing the numbers of Spanish speakers involved in public access computing at their local libraries. Participating library staff made gains in their individual abilities to understand differences in behaviors in the library (like wanting to work in groups at the computer instead of individually) and are more able to refer patrons to organizations in the community that can meet those needs the library cannot (immigration services, legal services, etc.).  Most impressive is that participating library staff made significant improvements in almost every measure of their skills, knowledge and abilities related to reaching out to Spanish speakers in their communities.

- Increase partnerships among local libraries and other community organizations serving Spanish-speaking residents. Building community partnerships with organizations that serve Spanish speakers was a key focus of the curriculum and the SLO Program as a whole, and 43% of workshop participants report starting a new partnership or strengthening an existing partnership with schools, cultural heritage organizations and health and human services providers.

- Impact the Hispanic community by increasing awareness about local library services and public access computing. In addition to increasing library outreach efforts to Spanish speakers, participating library staff built better cultural awareness and learned how to reach out more effectively. Participants report using community partnerships and the workshop how-to’s to improve the effectiveness of their marketing to the Spanish-speaking community with strategies like focusing on Spanish radio and sending flyers home with school kids.

- Continue to build and grow the Spanish Language Outreach online community at WebJunction for library staff to share content and information with each other, with the longer term goal of providing access to materials to a larger audience of local libraries through WebJunction. The Spanish Language Outreach Program has had a strongly positive effect on the WebJunction community and on the sustainability of the WebJunction organization. SLO program participants have been very active participants in the WebJunction community. The SLO Program has been a key driver of site traffic to WebJunction.org. The SLO webinar series (22 webinars to date) has been very popular, and more than 4,000 library staff subscribe to the monthly SLO email newsletter. The workshop has also been adapted into an online course, and 440 people have enrolled since the course went online in March 2006.

Recommendations for Future Programs

The top three resources that participants said would be key for furthering their outreach efforts were Spanish for Library Staff (54%), along with more information on partnering with community groups (41%) and more marketing tips and tricks (40%). Library staff also wished for more resources for those who are brand new to Spanish Language Outreach, and more resources, discussion and support for small struggling libraries trying to do outreach.

Trainers agreed that Spanish language skills for library staff would help library staff create a welcoming environment for Spanish speakers. Additionally, they recommended following up with additional rounds of the program to reach more library staff and to continue to develop the library staff skills of those who already attended, coaching and consulting for program participants to support and foster additional efforts to reach out to Spanish speakers, and help for participants to understand how to measure and evaluate an outreach effort, to make sure that those efforts are effective. Trainers and coordinators also recommended a course for boards and directors on why they should support special outreach efforts, and coordinating national campaigns for literacy, the value of libraries, or a national early literacy initiative, perhaps in connection with PLA’s Every Child Ready to Read.

Because WebJunction is uniquely positioned with a national perspective on Spanish speakers, SLO staff should continue their efforts to build best practices, host special events and build the community of practice around better serving Spanish speakers, and take advantage of any opportunity to help the library field understand the challenges and success of Spanish speakers in the U.S.

Now that the program’s goals have been achieved, the resources that have been developed by program staff, participants, trainers and consultants can be leveraged. Key resources:

- Curriculum: The SLO Program curriculum, especially community partnership development strategies and effective marketing techniques for reaching out to Spanish speakers, has been validated by community members via focus groups and Perceptions survey data.

- Online community and resource collection: WebJunction’s online collection on outreach to Spanish speakers is a recognized national source of tools and information, cited as a resource even by REFORMA, the key national association to promote library and information services to Latinos and the Spanish speaking. WebJunction should continue to build the collection and the community around the collection, using webinars, newsletters and other methods.

- Understanding of the current “state of the nation” for library staff knowledge, skills and abilities (KSAs) related to outreach to Spanish speakers.

- Trainer cohort: The 158 trainers and coordinators are a ready source of on-the-ground knowledge and insight and should be considered an important national resource that can be used in the future to roll out additional programs or to advise on future efforts and investments needed in this area.

- The Latino Perceptions survey instrument and baseline data on Latino library use and perceptions of libraries can be used to measure progress at local or national levels in reaching out to Spanish speakers.

WebJunction should consider focusing on seeking additional grants and investing in continuing to run on-the-ground national programs – it has been the best source of loyal, interested membership, goodwill and collection development to date.

# Text boxes

Attitudes, Skills and Beliefs

Before and After Workshops

0

1

2

3

4

5

1

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

Measures

PRE

POST

Very much like me

Not like me