## timeline
WebJunction Online Conference Project Timeline
|  | October | November |  | December |  | January |  |  |  | February (Conf 9,10)
| Roles (initials) | 2nd half | 1st half | 2nd half | 1st half | 2nd half | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Define Success Factors
WebEx and Calendar Prep
WebEx Admin Training | JP/KM/MP
Registration and Email Templates | JP
Update Evanced Email Templates | JP | In place before listing Dec events in Evanced |  | Update with WebEx if needed
WebEx Production Training | JP/SS/CRH/KM/MP | bar: January Week 3
LEU/CE credit request process developed | JP/KG/KM/SS
Site Prep
Registration workflow verified | JP
Conference Page(s) created | SS
Value-Add Conference options (action plans, learning plans etc) | Next time! | bar: January Week 1 to January Week 4
Content acquisitions from presenters and registrants | JP/SS | bar: January Week 4 to February (Conf 9,10) Week 2
Communication Plan
Site and Crossroads | JP/SS |  | Pick name |  | Announced in Crossroads | Registration announced on site | January Week 1: Additional write-up in Jan Crossroads; February (Conf 9,10) Week 4: Recap in March xroads
Partner communication | JP/RVN/KG | Partner Brief, Group in LSC |  |  | Encourage localized promotion
Update housekeeping/PSA slides for use in conference sessions | JP/KM | bar: January Week 4
Off site promotions | All
Presenter Recruitment
Speakers for Online Conference are booked | JP
Alternates booked - back up plan for "town hall" format established
Fill program calendar | JP
Logistics and Planning email | JP
Presenter Training | JP/KM/SS | bar: January Week 4 to February (Conf 9,10) Week 1
Followup
Email sent to all registrants | JP | bar: February (Conf 9,10) Week 2
Conference Evaluation/Survey developed | JP/SS | bar: January Week 2
Archives downloaded from WebEx | JP | bar: February (Conf 9,10) Week 2
Archive pages created | JP | bar: February (Conf 9,10) Week 2
Certificates sent out | KM | bar: February (Conf 9,10) Week 4

## schedule
Tuesday, February 9
Time |  |  |  | Presenters | Session | Production Staff Duty | Twitter Support
Pacific | Mountain | Central | Eastern
8:00-8:30 |  |  |  | WebJunction | Technical Testing
8:30-9:00 | 9:30-10:00 | 10:30-11:00 | 11:30-12:00 | WebJunction | Welcome
9:00-10:00 | 10:00-11:00 | 11:00-12:00 | 12:00-1:00 | Mala Muralidharan and Richard Prouty | Building Digital Community: Arizona Memory Project
10-10:30 | 11-11:30 | 12-12:30 | 1-1:30 | Break |  | Break
10:30-11:30 | 11:30-12:30 | 12:30-1:30 | 1:30-2:30 | Pat Carterette | Learning When There's No Time (or Money) to Learn
11:30-12:30 | 12:30-1:30 | 1:30-2:30 | 2:30-3:30 | Sandra Nelson | Strategic Planning
12:30-1:00 | 1:30-2:00 | 2:30-3:00 | 3:30-4:00 | Break |  | Break
1:00-2:00 | 2:00-3:00 | 3:00-4:00 | 4:00-5:00 | Kendra Morgan | Technology Planning
2:00-3:00 | 3:00-4:00 | 4:00-5:00 | 5:00-6:00 | Cindi Hickey and Janie Rutherford | Marketing library technology and via technology
Wednesday, February 10
Time |  |  |  | Presenters | Session
Pacific | Mountain | Central | Eastern
8:30-9:00 | 9:30-10:00 | 10:30-11:00 | 11:30-12:00 | WebJunction | Day 2 Welcome
9:00-10:00 | 10:00-11:00 | 11:00-12:00 | 12:00-1:00 | Joshua Dodson and Laura Slavin | WordPress for Library 2.0 and Beyond
10-10:30 | 11-11:30 | 12-12:30 | 1-1:30 | Break |  | Break
10:30-11:30 | 11:30-12:30 | 12:30-1:30 | 1:30-2:30 | Karen McCoy | Instant Message Reference
11:30-12:30 | 12:30-1:30 | 1:30-2:30 | 2:30-3:30 | Wendy Knapp (WebJunction-Indiana) and Mary Alice Ball | Indiana Connectivity
12:30-1:00 | 1:30-2:00 | 2:30-3:00 | 3:30-4:00 | Break |  | Break
1:00-2:00 | 2:00-3:00 | 3:00-4:00 | 4:00-5:00 | Stephanie Gerding | Library Grants 101
2:00-3:00 | 3:00-4:00 | 4:00-5:00 | 5:00-6:00 | Jennifer Fenton, Kirsten Furl and Ahniwa Ferrari | Hard Times Resources

## topics presenters
Session # | Topic Area | Focus | Presenter | Email | Position | Library/Org | website | Session Title | Session Description
1 | Staff training | "Learning When There's No Time (or Money) to Learn" | Pat Carterette |  |  | Georgia Public Library Service | http://www.georgialibraries.org/
2 | Marketing |  | Cindi Hickey |  |  | State Library of Kansas | http://www.kslib.info/index.html
|  |  | Janie Rutherford |  |  | State Library of Kansas
3 | Outreach, funding, advocacy | Library Grants 101 | Stephanie Gerding |  |  |  | http://www.stephaniegerding.com/
4 | Services and programming | Memory Project | Mala Muralidharan |  |  | Arizona State Library and Archives
|  |  | Richard Prouty |  |  | Arizona State Library and Archives
5 | Services and programming | Hard Times Resource Guide | WA - Jennifer Fenton |  |  | Washington State Library | http://www.sos.wa.gov/library/
|  |  | Kirsten Furl |  |  | Washington State Library
|  |  | Ahniwa Ferrari |  |  | Washington State Library | http://www.sos.wa.gov/library/hardtimes/Default.aspx
6 | Technology planning | Indiana connectivity | Wendy Knapp |  |  | Indiana State Library | http://www.in.gov/library/
Mary Alice Ball
7 | Technology planning |  | Kendra Morgan
8 | Virtual libraries | Instant Message Reference | Karen Long McCoy |  |  | Farmington Public Library (NM) | http://www.infoway.org/
9 | Library's web presence | Web/Library 2.0 features through WordPress (with TechSource) | Joshua Dodson and Laura Slavin |  |  | Lincoln Memorial University, Harrogate, TN | http://lmunet.edu/
|  |  | Laura Slavin |  |  | Lincoln Memorial University, Harrogate, TN | http://lmunet.edu/
10 | Strategic Planning | Strategic Planning | Sandra Nelson |  |  |  | www.sandranelson.com