Rural Library Sustainability Project: Key Points about Evaluation

# Audiences for Evaluation

- Bill & Melinda Gates Foundation

- WebJunction

- State Libraries

- State Coordinators & Trainers

- Local Participants

# Project Goals

- Increase number of librarians implementing sustainability action plans.

- Facilitate forum for local librarians participating to share best practices and develop next steps.

- Increase advocacy efforts by State Libraries.

- Increase number of librarians from small and rural libraries participating in WebJunction.

To Measure across Fifty States, We Need Your Help

You must think like scientists conducting an experiment, because we are looking for changes in attitude, knowledge, skill, behavior, or condition.  To see if there are changes, we need your help gathering data before and after participation.  We have allowed a five-month interval after the workshops to insure that participants have time to begin implementing the knowledge and skills they learned.

# Evaluation Tools We Will Use

- An online pre-assessment of each participant just before the workshop and similar online post-assessment five months afterwards. (Trainers have already experienced the online pre-assessment.) [State Coordinators/Trainers send pre-; WJ sends post-assessments.]

- A traditional end-of-workshop evaluation, to provide immediate feedback for trainers and early indicators for WJ staff.  (Trainers will also complete similar a similar end-of-workshop evaluation.) [You will disseminate, collect, and mail to WJ for data entry.]

- Phone interviews with Coordinators/Trainers after the first one or two workshops, around June 2006. [Evaluator Sara Laughlin will schedule a time to call you.]

- WJ usage data, before and after, including registration, page hits, course enrollment, and message board use, for each state and compared with aggregated non-participating states.

- In addition to these formal tools, we are always thrilled to have stories that can serve as examples, so don’t hesitate to share them with WJ staff or the evaluator at any time!

# Your Responsibilities

Before the workshop:

- Plan and market the workshops

- Collect participant names and e-mails during registration (accuracy is really important, as we will use the e-mail addresses to send the survey links)

- Send each participant a message 7-10 days before the workshop with a link to the pre-assessment and ask participant to complete it before coming.

At the workshop:

- Before beginning the workshop (perhaps during the arrival period) ask if any participants have not completed the online assessment. If some have not, ask them to complete a paper version.  Collect them.

- During the workshop, explain the importance of evaluation to this program and asks participants to complete both the workshop evaluation and the post-assessment that will be e-mailed to them in five months.

- At the end of the workshop, ask participants to complete the end-of-workshop evaluation form.  Collect them.

## After the workshop

- Send paper pre-assessments, (if you collected any at the workshop), along with end-of-workshop evaluations, to the Project Coordinator at the WebJunction-Seattle office.

Questions about Evaluation?

Sara Laughlin

812.334.8485

laughlin@bluemarble.net