Rural Library Sustainability Program: Important Dates

EVENTS						DATES

Curriculum Development Institute		February 27, 2006 – March 2, 2006

Workshops in each state			March 2006 – November 2006

Post Workshop Survey				begins August 2006

Expense Reports from Institute

Due to Project Coordinator			March 31, 2006

State Localization Plan

Due to Curriculum Developer			April 14, 2006

List of Workshop Dates & Locations

Due to Project Coordinator 			April 14, 2006

List of Participants attending the

Rural Library Sustainability Forum at

ALA in June 2007 -

Due to Project Coordinator			December 1, 2006